## Sheet1
PROJECT NAME: | TriLingua
TEST PLAN ID: | TL-AT2-TP-01
CREATED BY: | Capstone group (names to be entered)
DATE OF CREATION: | 2026-09-29
DATE OF REVIEW: | TBD
TEST ITEM | TEST STRATEGY | TEST TYPE | FEATURES TO BE TESTED | FEATURES NOT TO BE TESTED | ENTRY CRITERIA | EXIT CRITERIA | DELIVERABLES | START DATE | END DATE | ASSIGNEE | RISK ANALYSIS
Account and roles | Functional and security | Functional / security | Register, sign in, reset, account, role and owner access | Live Google OAuth delivery | Isolated users; mail sandbox; roles provisioned | TC01–TC05 pass; no data leak | Case log, defect log | TBD | TBD | Group member TBD | Reset delivery and access control
Text translation | Boundary and integration | Functional / integration | Six directions, validation, persistence indication | Human quality conclusion from automated output | Live provider and held out texts | TC06–TC07 pass; save status truthful | Outputs, case log | TBD | TBD | Group member TBD | Provider availability and language variance
Document intake | Format matrix and negative tests | Functional / security | Nine configured formats, signature, size and quota | Unadvertised formats | Safe fixtures; isolated storage and quota | TC08–TC09 pass | Upload log, defects | TBD | TBD | Group member TBD | Unsafe file or quota bypass
Job lifecycle | End to end and interruption | Integration / recovery | Polling, worker crash, retry, duplicate prevention | Production stress at this stage | Isolated PostgreSQL queue; two workers | TC10–TC11 pass | Job state log | TBD | TBD | Group member TBD | Race or lost job state
Output and storage | Open file and failure injection | Functional / recovery | Download, rendering, missing object, signer failure | Unsupported viewer apps | Target apps and primary/fallback storage | TC12–TC13 pass; files open | Rendered comparison | TBD | TBD | Group member TBD | Dead link or layout loss
History and dashboard | User workflow and scale boundary | Functional / data integrity | History actions, totals, 201+ records | Analytics beyond listed cards | Seeded isolated records | TC14–TC15 pass | Case log, count evidence | TBD | TBD | Group member TBD | Capped totals or missing records
Admin review | Concurrent review and audit | Functional / integrity | Text/document edits, publish, conflict, audit | Reviewer role separate from admin | Admin test accounts; review fixtures | TC16–TC18 pass | Review and audit log | TBD | TBD | Group member TBD | Stale overwrite or wrong published file
Resilience and acceptance | Fault injection and human review | Recovery / usability | Provider/storage failure, cleanup, quality, accessibility | Production release approval | Fault harness; bilingual reviewers; browsers | TC19–TC22 pass; quality threshold agreed | Defects, reviewer sheets, accessibility record | TBD | TBD | Group member TBD | Unverified quality and live deployment
PROJECT OVERVIEW
TriLingua is a capstone web application for AI assisted text and document translation among English, Filipino, and Cebuano. A regular user can translate text, submit documents, track jobs, view history, and download results. An administrator can review translations, manage failed jobs, inspect users, and view audit records. This assessment defines tests; it does not report new execution results or establish translation accuracy.
FEATURES IN SCOPE
1. Guest registration, sign in, password reset, account settings, and role restricted pages
2. Text translation among English, Filipino, and Cebuano, with saved history
3. Document upload, validation, asynchronous processing, status polling, retry, and download
4. History, documents, bookmarks, priority flags, notifications, and dashboard activity
5. Administrative text and document review, publication, job management, users, and audit log
METHOD AND RELEASE GATES
Test environments: isolated Laravel/Python stack, test database, safe mail, document storage, queue workers, and target document viewers.
Record evidence for each run: build or commit, date, tester, actual result, defect ID, and screenshots or files where relevant.
Entry: a deployable test build, seeded role accounts, safe fixtures, live provider for integration cases, and bilingual reviewers for TC21.
Exit: critical security/data-loss cases pass; remaining defects are documented; all 22 planned cases are executed or explicitly deferred.
Translation quality, accessibility, load, real storage, and two-worker behavior require separate live or human acceptance. This plan records no new pass result.
Source baseline: routes/web.php; config/translation.php; docs/CURRENT_SYSTEM_REEVALUATION_2026-09-29.md. Schedule and group assignees await course coordination.